## Slide 1
DCCS/MSCoE Surgeon Operational Design - 2027
Deliver reliable, high-quality healthcare that exceeds DHA standards for access and performance.
2025 Current State
GLWACH is a reactive system underperforming on DHA scorecards, where critical staffing shortages create mission-failure risk, unsustainable primary care access, and an overloaded ER. These systemic performance gaps, compounded by a lack of unit-level safety accountability, strain the MSCoE partnership and directly hinder the training mission.
2027 Desired State
Be a High Reliability Organization consistently meeting DHA standards, where an integrated trainee care model and technologically empowered staff deliver the right care, right place, right time, protect the ER, and drive clinical efficiency. This foundation reinforced by accountable unit leaders, will forge a fully integrated partnership with MSCoE that directly enables the training mission.
Medically Ready Force
Develop and empower a professional, technologically proficient, and resilient medical team capable of executing the mission with initiative.
Ready Medical Force
Synchronize medical functions to support the MSCoE training mission by ensuring trainees receives the right care, right place, right time.
MSCoE Integration
Optimize Critical Services PC Access, ER flow, 3SL- 176
Implement care ladder: Medic-> CSSP-> NP->Doc
Designate No-Fail mission: Hospital services/OB>Gyn
Phase 1
Build
Now – 1Mar26
Phase 2
Improve
1Mar – 1Oct26
Phase 3
Refine
1Oct20- July 27
HQ: PCSL, ER, 3SL, BH, Cred
Main Effort: Phase 2
HQ: DCCS Leaders
Main Effort: Phase 3
HQ: TOMS, CTMC, BH, ER
Main Effort: Phase 1
PCSL DHA Care model (Access / HEDIS)
ER/3SL: Improve Through put in New Facility: ER Fast track (medic lead)
BH: Improve BH Targeted Care Model BH
Refine PCSL flow- PI project to conduct root cause analysis of issues.
Refine and optimize 3SL surgery through put bottle necks (root cause analysis)
technology intergrated into day-to-day practice to ensure highest standard
Introduce Efficiency Tools (AI & PowerBI)
Clarify Roles: Right people right job, right direction. DELIBERATE COUNSELING
Accountability: Credentials, Safety standards
Conduct Functional Needs analysis
Standardize medical operations: Standardize key documents, training exercise OPORDS medical Annexes, BAS SOPs.
Establish predicative medical logistics : DCAM trained medics, ASL, burn rates, TDA to match FORCOM
Develop Automated Readiness tracker: Vantage to PowerBI medical readiness dashboard
Reorganize Clinic for Efficiency
Manning Functional Need: RN/SW & APPs
Continue to intergrade Telehealth and asynchronous encounters
Implement a Deliberate Professional Development Model
Prioritize Military Skills and Education
Execute deliberate leadership transition plan
Implement Trainee care model: TOMS/CTMC/ER
Establish MSCoE Surgeon Oversight: sync across BDEs
Executive Med: MSCoE Key Leaders care
Protect Clinic Access: SRP walk ins, Shaving/Body fat Group encounters
Institutionalize a continuous improvement loop
Integrate Medical Readiness into the MSCoE Battle Rhythm
Achieve Predictive Medical Logistics
Projected Date: July 2027
Decisive Point 1: Hospital Move
Decisive Point 2: Change of Command
Mission: Continuously synchronize medical efforts across the GLWACH and MSCoE footprint to deliver the right care, at the right place, at the right time—building a medically ready force, developing a ready medical force, and achieving seamless MSCoE integration—in order to enable the MSCoE training mission.
Notes: Phase 1: Build (Now – 1 Mar 2026): This initial five-month phase focuses on stabilizing critical systems and processes before the move to the new hospital. The main effort is LOE 3: MSCoE Integration, with the immediate priority of implementing the 'Right Care, Right Place, Right Time' model for trainees to fix systemic performance gaps. The decisive point for this phase is the successful move into the new hospital facility.
LOE 1: Medically Ready Force
  Optimize Critical Services: Execute plans to fix Primary Care access, trainee ER flow, and Surgery throughput. Increase Group encounters (Shave/Body Fat)
  Designate No-Fail Missions: Prioritize critical hospital services like the OB mission and the trainee Behavioral Health mission to prevent catastrophic failure.
  Implement Care Ladder: Institute the "care ladder" model across clinics, ensuring patients are seen at the right level of care (medic, nurse, PA/NP, physician) to optimize provider time .
LOE 2: Ready Medical Force
  Introduce Efficiency Tools: Conduct initial Leader Professional Development (LPD) sessions on AI tools (OpenEvidence/Ask Sage) to build user familiarity and drive efficiency
  Clarify Roles: Right People, Right Job: Ensure the right people are in the right jobs by clearly defining critical roles and responsibilities, such as CTMC OIC, and deliberate counseling.
  Establish Accountability: Credentials and Safety standards: Enforce 100% BLS compliance and timely medical record closure (72-hour outpatient / 30-day inpatient rule), no pencil wiping credentials committee, risk management.
  Conduct at functional Need anslysis: To support the Care ladder approach preform a function needs analysis to increase manning of Nurses/SW and APP (PA/NP) over Physicians/PHDs
LOE 3: MSCoE Integration (Main Effort)
  Implement Trainee Care Model: Execute the three-pronged approach (TOMS, CTMC, ER) to deliver the right care, at the right place, at the right time.
  Establish Surgeon's Oversight: Restructure the MSCoE medical line of effort to establish the Surgeon as the lead for synchronizing manning, training, and equipping across all brigades to identify and fill readiness gaps.
  Institute Executive Medicine: Establish and manage an Executive Medicine program to provide dedicated, streamlined healthcare access and readiness oversight for MSCoE key leaders.
  Protect Clinic Access: Enforce the Soldier Readiness Program (SRP) as the single, walk-in point for all readiness tasks (PHAs/physicals) to protect primary care templates with group shaving and Body fat encounters
Phase 2: Improve (1 Mar 2026 – 1 Oct 2026) Following the hospital move, this seven-month phase shifts the main effort to LOE 1: Medically Ready Force. The focus is on leveraging the new facility and stabilized processes to drive performance and achieve all DHA metrics. This phase culminates at the decisive point of the Hospital Commander's Change of Command.
LOE 1: Medically Ready Force (Main Effort)
  PCLS DHA Care model: Building on the initial stabilization of access, drive performance to meet DHA targets for appointments (<24hr acutes / <7d follow-up) and 100% HEDIS completion.
  Improve Throughput in New Facility: Leverage the new hospital to implement the ER fast-track model (medic lead) and optimize OR scheduling, moving from stabilized to targeted throughput of 176 cases/month.
  Improve BH Targeted Care Model: Scale the group therapy and technician-led vectors established in Phase 1 to expand access and meet readiness obligations with fewer providers.
LOE 2: Ready Medical Force
  Man to the Function needs analysis: Man to the Care Ladder model - off the function needs analysis conducted in Phase 1 -> increase RN/SW and APP (PA/NP) over physicians and PHD across service lines exception: Surgeon. Transition from the reactive manning of Phase 1 by building a predictable 6-month staffing model to anticipate deployment and PCS backfills.
  Reorganize for Clinical Efficiency: Based on the stabilized processes from Phase 1, restructure clinic operations, provider templates, and empanelment to maximize efficiency in the new facility.
  Integrate Telehealth and Asynchronous encounters: Move beyond ad hoc use by formally leveraging credentialed telehealth providers and increase asynchronous capabilities to augment staff, cover service gaps, and reduce network leakage.
LOE 3: MSCoE Integration
  Establish Predictive Medical Logistics: Transition from reactive to predictive logistics by creating brigade Authorized Stockage Lists (ASLs), tracking usage rates, refining the TDA to match FORSCOM standards, and empowering a DCAMs-trained medic in each brigade to manage a data-driven spend plan.
  Standardize Medical Operations: Formalize MSCoE Surgeon oversight of all brigades by organizing CTC medics under a central authority and standardizing key documents, including training exercise OPORDs and Battalion Aid Station (BAS) SOPs .
  Develop Automated Readiness Tracker: Build an automated readiness tracker by creating a data pipeline from Army Vantage to a Power BI dashboard, enabling real-time oversight of key medical readiness metrics across all brigades.
Phase 3: Refine (1 Oct 2026 – 1 Jul 2027): In this final nine-month phase leading to my PCS, the focus shifts to refinement and sustainment, with the main effort on LOE 2: Ready Medical Force. The goal is to move beyond simply meeting metrics to deeply embedding a culture of continuous improvement, ensuring the systems we've built are not just maintained but are actively refined. This phase prepares the organization for a successful leadership transition by ensuring the team is empowered to own and lead the established processes.
LOE 1: Medically Ready Force
  Refine Primary Care Flow and Access Charter a formal PI project to conduct a root cause analysis of Primary Care Service Line (PCSL) inefficiencies impacting patient flow. This project will target the systemic issues causing poor access to care and unmet HEDIS measures, ensuring we achieve and sustain our core DHA metrics .
  Optimize Surgical Service Line Throughput Conduct a root cause analysis of the Surgical Service Line (32SL) to identify and eliminate throughput bottlenecks from consult to recovery. The analysis will focus on anesthesia constraints, first-case on-time starts, and OR turnover times to drive the monthly case volume to the DHA target of 176 .
  Integrate Technology to Enhance Standards of Care Integrate clinical decision support tools like OpenEvidence and other AI technologies into daily workflows at the point of care . This will enhance diagnostic accuracy and streamline documentation, ensuring our providers are equipped to deliver the highest, most evidence-based standard of care.
LOE 2: Ready Medical Force (Main Effort)
  Execute Deliberate Professional Development Publish and execute a six-month Leader Professional Development (LPD) calendar and mandate quarterly deliberate counseling sessions for every team member. This provides a predictable framework for continuously reinforcing goals and expectations, tracking individual progress, and ensuring a clear path for professional growth.
  Enforce Military Readiness and Education Standards Actively track and manage soldier readiness by scheduling required Army training and prioritizing attendance at professional military education (PME) for all eligible personnel. This non-negotiable standard ensures we develop well-rounded leaders who are not only clinical experts but are also prepared for future Army leadership roles.
  Execute a Deliberate Leadership Transition Plan Identify and formally mentor high-potential subordinates to take ownership of key processes, such as leading PI projects and briefing performance dashboards . This direct transfer of responsibility is the final step in linking individual development to organizational sustainment, guaranteeing continuity of our operational model after the change of leadership.
LOE 3: MSCoE Integration
  Institutionalize a Continuous Improvement Loop Establish a formal process to conduct after-action reviews (AARs) following all major MSCoE training exercises to capture medical lessons learned. This ensures that medical support plans, MEDLOG, and Battalion Aid Station (BAS) SOPs are continuously refined based on real-world feedback, creating a truly responsive and mature system.
  Integrate Medical Readiness into the MSCoE Battle Rhythm Transition the automated readiness tracker from a reporting tool to a predictive planning tool, briefing key trends at the quarterly MSCoE medical readiness council. This ensures medical readiness is a permanent, data-driven topic in the MSCoE command dialogue, solidifying a seamless and proactive partnership.
  Achieve Predictive Medical Logistics Refine the brigade-level spend plans based on a full year of consumption data from the Authorized Stockage Lists (ASLs). This final step moves the brigades from data collection to true predictive logistics, ensuring they can anticipate future needs and manage their resources effectively.